## Project Development Schedule
Agency: Shasta Regional Transportation Agency
Project: North State Intercity Bus System
PROJECT DEVELOPMENT SCHEDULE
| 2017 | [5 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [15 empty] | 2021
Activities | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J
Pre-Award Business Plan (July 2017-May 2018) | bar: 2018 A to 2018 M
1. Project management (June 2018-July 2021) | bar: 2018 A to 2018 A; 2018 N to 2021 J
1.1. Administration of North State Intercity Project (TIRCP Grant funded items) | bar: 2018 A to 2018 A; 2018 N to 2021 J
1.2. Quarterly progress reports | bar: 2018 J; 2018 D; 2019 M; 2019 J; 2019 S; 2019 D; 2020 M; 2020 J; 2020 S; 2020 D; 2020 M; 2021 J
1.3. Invoicing | bar: 2018 A to 2018 A; 2018 N to 2021 J
1.4. Project Delivery Report | bar: 2018 A to 2018 A; 2018 N to 2021 J
1.5. Final report of expenditures and project closeout | bar: 2020 A to 2021 J
2. Project Implementation (July 2018-February 2021) | bar: 2018 M to 2018 A; 2018 N to 2021 J
2.1. Prepare agreements with project partners (July 2018-Oct. 2018) | bar: 2018 M to 2018 A
2.1.1.San Joaquins Joint Powers Authority | bar: 2018 M to 2018 A
2.1.2.Capital Corridor | bar: 2018 M to 2018 A
2.1.3.Lake Transit Authority | bar: 2018 M to 2018 A
2.1.4.Redding Area Bus Authority | bar: 2018 M to 2018 A
2.1.5.Glenn County Transportation Commission | bar: 2018 M to 2018 A
2.1.6.Siskiyou County Transportation Commission | bar: 2018 M to 2018 A
2.1.7.Adobe Road transit stop location partner | bar: 2018 M to 2018 A
2.1.8.Williams transit stop location partner | bar: 2018 M to 2018 A
2.1.9.Sacramento International Airport | bar: 2018 M to 2018 A
2.1.10. City of Sacramento | bar: 2018 M to 2018 A
2.1.11. Sacramento Regional Transit | bar: 2018 M to 2018 A
2.2. Construction (July 2018-September 2019) | bar: 2018 J to 2018 A; 2018 N to 2019 O
2.2.1.Vehicles | bar: 2018 J to 2018 A
2.2.1.1. Procurement solicitation | bar: 2018 J to 2018 A
2.2.1.2. Lease/buy contracting | bar: 2018 A
2.2.1.3. Amenities and equipment | bar: 2018 A
2.2.2.Backbone storage/maintenance/charging facilities | bar: 2018 J to 2018 A; 2018 N to 2019 F
2.2.2.1. RABA maintenance facility | bar: 2018 J to 2018 A
2.2.2.2. Williams opportunity charging station | bar: 2018 N to 2019 F
2.2.2.3. Sacramento under freeway location | bar: 2018 N to 2019 F
2.2.3.Backbone System stop improvements | bar: 2018 N to 2019 F
2.2.3.1. Downtown Redding Transit Center | bar: 2018 N to 2019 F
2.2.3.2. Adobe Road stop improvements | bar: 2018 N to 2019 F
2.2.3.3. Williams stop improvements | bar: 2018 N to 2019 F
2.2.3.4. Sac Valley Station and SMF Improvements | bar: 2018 N to 2019 F
2.2.3.5. Capital Mall @7th Street improvements | bar: 2018 N to 2019 F
2.2.4.Feeder system vehicles | bar: 2018 J to 2018 A
2.2.4.1. Procurement solicitation | bar: 2018 J to 2018 A
2.2.4.2. Lease/buy contracting | bar: 2018 A
2.2.4.3. Amenities and equipment | bar: 2018 A
2.2.5.Feeder system maintenance/storage/charging facilities | bar: 2018 N to 2019 F
2.2.5.1. Siskiyou County maintenance/storage/charging facility | bar: 2018 N to 2019 F
2.2.5.2. Lake Transit maintenance/storage/charging facility | bar: 2018 N to 2019 F
2.2.5.3. Glenn County maintenance/storage/charging facility | bar: 2018 N to 2019 F
2.2.5.4. Shasta Urban maintenance/storage/charging facility | bar: 2018 N to 2019 F
2.2.6.Feeder system stop improvements | bar: 2018 N to 2019 J
2.2.6.1. Redding circulator stop improvements | bar: 2018 N to 2019 J
2.2.6.2. Siskiyou County stop improvements | bar: 2018 N to 2019 J
2.2.6.2.1. Yreka | bar: 2018 N to 2019 J
2.2.6.2.2. Weed | bar: 2018 N to 2019 J
2.2.6.2.3. Mt. Shasta | bar: 2018 N to 2019 J
2.2.6.2.4. Dunsmuir | bar: 2018 N to 2019 J
2.2.6.3. North Valley feeder stop improvements | bar: 2018 N to 2019 J
2.2.6.3.1. Willows | bar: 2018 N to 2019 J
2.2.6.3.2. Orland | bar: 2018 N to 2019 J
2.2.6.3.3. Corning | bar: 2018 N to 2019 J
2.2.6.4. Lake County feeder stop improvements | bar: 2018 N to 2019 J
2.2.6.4.1. Transit hub in Clearlake | bar: 2018 N to 2019 J
2.2.7.Charging infrastructure | bar: 2018 M to 2018 A; 2018 N to 2019 J
2.2.7.1. Design | bar: 2018 J to 2018 A
2.2.7.2. Environmental review | bar: 2018 M to 2018 A
2.2.7.3. Procurement | bar: 2018 J to 2018 A; 2018 N to 2018 D
2.2.7.4. Buy/Lease option analysis | bar: 2018 J to 2018 A; 2018 N to 2018 D
2.2.7.5. Site prep | bar: 2018 J to 2018 A
2.2.7.6. Construction | bar: 2018 A; 2018 N to 2019 A
2.2.8.Ticketing infrastructure | bar: 2018 J to 2018 A
2.2.8.1. Procurement process | bar: 2018 J to 2018 A
2.2.8.2. Purchase equipment | bar: 2018 A
2.2.8.3. Installation | bar: 2018 A
2.2.8.4. Testing and launch | bar: 2019 A to 2019 O
2.3. Launch Marketing (July 2018-March 2021) | bar: 2018 J to 2018 A; 2018 N to 2020 O
2.3.1.Marketing plan | bar: 2018 J to 2018 A; 2018 N to 2018 D
2.3.2.Branding/Graphics | bar: 2018 N to 2019 M; 2019 S to 2019 O
2.3.3.Marketing materials | bar: 2019 F to 2020 O
2.3.4.Media | bar: 2019 J to 2020 O
3. Performance Monitoring (September 2019-November 2033) | bar: 2019 J to 2021 J
3.1.1.Performance monitoring system development | bar: 2019 J to 2019 O
3.1.2.Data collection | bar: 2019 J to 2021 J
3.1.3.Vehicle analysis | bar: 2019 J to 2021 J
3.1.4.Monthly data summaries | bar: 2019 J to 2021 J
3.1.5.Technical evaluation @ 3 mo., 6 mo., 1 yr., and then every 6 months | bar: 2019 J to 2021 J
3.1.6.Final project performance evaluation | bar: 2021 M to 2021 J
4. Begin North State Intercity Bus Service (Oct. 2019) | bar: 2019 O