## Instructions
Instructions
The Proposer must complete each worksheet in this file completely. Printed versions of each completed Excel form must be included in the hardcopy version of the Contractor’s Price Proposal. In addition, the completed Excel forms must be saved to the appropriate USB package in both Excel and PDF formats with the Proposer’s response.
Handwritten forms will not be accepted.
For each form, fill in the yellow highlighted sections. If you have any difficulty in completing these forms, please contact the Agency Contact.

## Milestone Schedule
Shasta Regional Transportation Agency
RFP 2019-01
CER 12 - Minimum Milestone Plan
Proposing Company Name
Expected Notice of Intent to Award: April 24, 2019
Bus Build and Delivery
| Milestone | Desired End Date | Proposed End Date
| Pre-Production Meeting | -
| Begin Production | -
| Deliver Pilot Coach | -
| Deliver Last Coach | 2019-10-10
| Deploy Coaches in Revenue Service | 2019-10-31
EVSE Option A: Charging Equipment Only (if proposed)
| Milestone | Desired End Date | Proposed End Date
| Chargers Delivered to all 3 Charging Locations | 2019-08-15
EVSE Option B: Site Design, Charging Equipment, Installation, & Commissioning (if proposed)
| Milestone | Desired End Date | Proposed End Date
| Conceptual Design & Site Plan at all 3 Charging Locations Presented to Agency | -
| Engineering Design & Detailed Site Plan Completed | -
| Chargers Delivered to all 3 Charging Locations | 2019-08-15
| Chargers Installed at all 3 Charging Locations | 2019-08-31
| Chargers Commissioned at all 3 Charging Locations & Approved for Operation | 2019-09-30